## Basic Gantt Chart
Gantt Chart for MCSPROJ, PROJMAN & SOFTDEV
No. | TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Document Creation and Revision
1 | Project System Architecture | 2020-05-15 | 2020-05-16 | 2 | Lean | 20%
2 | Project's User Interface Design | 2020-05-05 | 2020-05-25 | 21 | Cholo | 60%
3 | Project Documentation V2 |  |  |  |  | 0%
4 | Project Documentation V3 |  |  |  |  | 0%
5 | Project Documentation V4 |  |  |  |  | 0%
6 | Project Documentation V5 |  |  |  |  | 0%
7 | Consolidated Project Documentation | 2020-06-06 | 2020-06-10 | 5 |  | 0%
Formulas:
DURATION (WORK DAYS) = DATEDIF([START DATE],[END DATE],"d")+1

## Sheet1
Project Status
No | TASK NAME | PERCENT COMPLETE
1 | System Notification | 40%
2 | Document Creation | 10%
3
4
5
6